Supporting Authority Group

MINUTES - 02/10/2024

Actions

- Statement to SAs regarding pre-election impacts

- Provide early sight of drafts to SAs as soon as feasibly possible and ahead of the pre-consultation period

- Existing early LNRS outputs to be published on the website during October 2024

- Arrange and undertake to deliver webinars to District Councillors of Supporting Authorities in each of the two RAs

- Introduction

Three Apologies were received

No matters arising not picked up in later this meeting.

- Update: General update & next steps

Defra and guidance – nothing significant since last meeting.  Awaited:

  - A recent Defra Q&A webinar gave the RAs an opportunity to air some views and seek answers

  - Regarding guidance on how LNRS will interface with Local Plans NE regionally noted:

    - the Levelling Up and Regeneration Act created requirements for various plan-making processes to “take account” of LNRSs. However,

    - the relevant sections of the LURA have not yet been commenced and form part of wider reforms to the planning system so the requirement to “take account” is not yet in force.

    - The Government has stated that they do intend to proceed with the reforms that would enable the requirement to “take account” of LNRSs, however timelines are uncertain.

    - Regards: How the LNRS will be implemented & the role of the RA, this was asked of the Gov’t by LNPs nationally…  In a Ministerial letter Mary Creagh MP PU-SoS for Nature - Confirms that:

      - delivery will be through join up with other funding sources.

      - regards co-ordination of implementation: Gov’t are developing options in advance of the next spending review AND exploring options for private finance to delivery priorities.

Project

- The project plan has recently been reviewed in the light of outstanding tasks and the impact of the pre-election period.

- We are still aiming to deliver a pre-consultation draft in the new year but it’s likely to slip to the end of January.  Caveats remain.

- Key Issue: County Elections 1st May 2025.

    - Following a meeting with the 3 Democratic Service managers from both RAs regarding the Pre-election period for 2025 it was noted that public facing activities will be strictly applied; this will have a substantial impact on the timing for final publication.

    - Constraints: that we must work within

      - Strict Pre-Election controls from mid-March

      - Likely to be an informal Pre-Election Period from January

    - Impacts:

      - We will likely be refused entry into the public space to conduct a consultation probably between Jan and May and definitely refused between March and May.  Current Timing:

        - Progress at present leads to the RAs seeking SA approval between Jan-end and Feb-end 2025

        - following amends, design and preparatory webinars etc, the public consultation could start April 2025

        - This puts the public facing component in the middle of the pre-election period.

      - Any significant change as a result of the elections will cause further delays.

      - In a worst case scenario should the publication be pushed to the Autumn there is every likelihood that further government guidance will be released affecting LNRS possibly requiring a further consultation with Supporting Authorities.

    - The approval process of the Pre-consultation draft with Supporting Authorities is unlikely to be affected

Engagement

- Closing surveys/initiatives on the website but will be keeping the web-tool that is collating projects open.

- 3 workshops to come for catchments partnerships, wellbeing organisations and delivery partners (No.3).

Description and measures

- Description: Review by TRP of the second draft of the description mid to late November, to be shared with SAs

- Following delivery partner workshop No.2: Priorities and associated outcomes in the next two weeks & measures are being drafted for November

Communications within Supporting Authorities:

- Offer of webinars for Councillors broadly welcomed. One for East Sussex and one for West.

- Engagement activities &

- Priorities & Measures: update and overview and outcome of the recent delivery partner’s workshop (KC)

- Description: Brief overview of the recent meeting with the Technical Review Panel

Double click the insertion below for the PDF slides for agenda items 3, 4 & 5

6.	Engaging with Members

- Following queries from Elected Members, district and county, around how they can be further involved.

- Questions arising:

    - How are SAG members dealing with delegated authority? Is it just for the pre-consultation draft?

    - Are they still expecting to formally sign off the pre-publication version?

    - If so, we need to know as soon as possible.

- Do we need to run some webinars for SAG Councillors?

- General discussion, agreement that a webinar would be welcomed.

- Action: LNRS Team to explore options.

Actions

- Statement to SAs regarding pre-election impacts

- Provide early sight of drafts to SAs as soon as feasibly possible and ahead of the pre-consultation period

- Existing early LNRS outputs to be published on the website during October 2024

- Arrange and undertake to deliver webinars to District Councillors of Supporting Authorities in each of the two RAs

AOB

- Confirmation given that BNG was covered in farmer briefings

- 3 harbours strategy was published Monday 30 Sept. 2024

- NPPF consultation is now closed

- Chichester DC Local Plan examination on their Local Plan is underway (Hearings started 01/10/2024)