Supporting Authorities Group Meeting

MINUTES - 2pm: 02/07/2025

Chair: Don Baker, West Sussex Responsible Authority

ATTENDEES

WSCC

ESCC

Sussex Local Nature Partnership

Wealden DC

Lewes & Eastbourne Councils

Mid Sussex DC

Natural England

Rother DC

Adur & Worthing Councils

Hastings BC

- WELCOME & INTRODUCTION

No matters arising.

Apologies: Horsham, Chichester (stand in), Brighton & Hove, Crawley, Rother (stand in)

- Update (Don Baker)

See embedded slide pack

National matters:

- Letter from Defra LNRS team incl communication from Minister. Any funding for RAs for FY25/26 will be appropriately used to transition to delivery. Need a robust, time-bound pathway to publication before Dec 25 or shortly after.

- Conditional: £135.5K dependant on publication. Further funding dependant on June's CSR outcomes.

- Letter also outlines roles of Strategic Authorities and RAs.

- Assuming further guidance is to come but not nec expecting it.

- RA delivery role: i) leading and convening a delivery partnership; ii) linking with LA services to promote use of LNRS in other decision making; iii) Identifying, developing and publicising projects; iv) track activities or projects delivering LNRS priorities.

- Some uncertainty over strength of conditioning over funding.

- Don to circulate letter and RA newsletter with minutes.

- Defra have offered support of ALBs, esp NE, but ALBs under significant pressure.

- RAs meeting Defra 09/07/25. To discuss delivery and associated dates and transition to delivery.

- RA newsletter incl benchmarking on RA progress across country.

- Shows Sussex in bottom 25% in terms of delivery timetable, but the two bottom categories are those we combined in our own benchmarking.

Timeline:

- Aiming to starting SA consultation on 18/08/25.

- NE panel - have requested date in first week of September.

- Should keep us on track for public consultation in October.

- Main issue around publishing by December is internal governance.

- Mapping (Kate Cole)

Measures and mapping

- Making some minor tweaks as a result of mapping process. Not significant changes.

- Have been split into East and West. Most of the measures are the same. Targeting, case examples obviously differ.

- Adding in priority species for each priority, aligning to measures.

- Mapping - follow up meetings after workshop based on themes. Done for water, coastal protected sites, grassland, farmland and heathland. Woodland this Friday. Urban on 14/07/25.

  - Agreeing preferred way of mapping + plan B with more targeting. May have to fall back to this once we have added everything together.

  - "Mash-up" meeting 21/07/25. To review ACIB and where there are overlapping measures.

  - Between 21/07/25 and 18/08/25, will be refining maps, generating ACIB etc.

  - Working on the assumption that we can provide GIS layer and mapping document for SAG consultation.

  - Technical document will explain decisions made during mapping.

  - CK: Confirmed that SAG consultation was a high level process of SAs saying whether the public consultation could go ahead or not. SDNPA have detailed comments at public consultation.

  - ES: Clarification that it is the SAG pre-public consultation 28 day period that is due to start on 18/08/25.

- Draft LNRS outline (Di Alcroft)

See embedded slide pack

Draft LNRS outline

- Overview of timeline.

- Currently in writing, editing and design stage.

- Also currently preparing for public consultation. May be preparing additional assets to help the process.

- Briefing note for elected members around beginning of August. Thanks to Jane Goodall for feeding into this.

- Promotion of LNRS:

  - Series of webinars: Town and parish councillors; Farmers; Public.

  - Additional activity with land agents and farmer advisors.

  - Social media toolkit.

  - For those without digital access - library briefings + hard copies in RA offices.

- What to expect:

  - 4 documents per LNRS area, each 50-100pages.

  - Aiming to share drafts over next couple of weeks. Mix of word docs and powerpoint (with interim design).

- Part 1: Essentially provides context.

- Part 2: Principles, opportunities, priorities and measures, maps. Maps will follow.

- Part 3: Species priorities and measures.

- Part 4: Technical methods - how we did it.

- JB: Briefings - anything for officers? Likely to use the September LAN webinar. How robust is the priority habitat data? Varies. Often don’t know the condition. May also be a reason for not mapping, e.g. lowland meadow. Intend to explain confidence around datasets in technical document. Reminder that this is the 1st iteration.

- LN: How does mapping fit into the structure? Confirmed static maps will be within Part 3, then link to online map. We will also provide GIS layers to SAs to overlay with their own data.

- AOB

There was no other business